Project Proposal for the Creation of Masterclasses on Art, Design and Technology in the Arab States.

# Rationale

Information and communication technology is influencing more and more creative practices.  An academic infrastructure is central to formalize the development of the emerging alliance of information technology with Art and design.  By creating a Masterclass on Art, Design and Technology in the Arab States, UNESCO is contributing to bridging the gap between University spheres of computer science and that of Art and design.

Opportunities for learning across multiple disciples are rare as universities and education institutes focus mostly on established disciplines such as Art, design, computer sciences, etc.  The Masterclass programme will contribute to the establishment of resources and contents for teaching purposes in the field of Art, Design and Technology, training post graduate students in the use of new digital technology in its application to the digital environment, reflecting the cultural and linguistic wealth of the Mediterranean Rim and the Gulf region.

This project will have three phases:

First Phase – 2004.

- Creating a sustainable infrastructure for the project (research of partners, collaborators), and drafting of a masterclass in digital cinema, interactive media, animation, interaction and communication design and sound art / design.

Second Phase – 2005.

- Holding a pilot masterclass in Beirut devoted to digital cinema, interactive media, animation, interaction and communication design and sound art / design (master classes, online seminars, etc.).

Third Phase – 2006-2007.

- Developing regional masterclasses in the Arab Region in the fields of Art, Design and Technology by establishing a theoretical foundation for it and explore the potential for constructive interaction between the concerned fields.

## Goals

Following the Declaration of Principles and Plan of Action of the World Summit on the Information Society (WSIS) in Geneva 2003, UNESCO engages in the promotion of training and human resource development in the use of ICTs in higher education institutes.  New training opportunities are created in the field of Art, Design and Technology through cooperation agreements between international and regional stakeholders such as UNESCO, Leonardo and cultural and educational institutes and/or universities in the Region or the Mediterranean Rim.

Capacity building should however not focus on connecting regions to information and communication technology, but rather to assist in the new creative expression and use of the infrastructure and thus support local content development of digital media production in the Arab region.  It is important to provide content that is relevant to the cultures and languages of individuals in the Information Society, through access to traditional and digital media services.

Full use is made of regional and international cooperation opportunities by transferring specialized knowledge thus removing barriers to equitable access to information.  International and regional dialogue should contribute to national capacity building in the fields of Art, Design and Technology.

## Outputs

The first phase of this programme will be devoted to the development of masterclasses, in the fields of:

- interaction and communication design

- digital audio and video production

- art and design methodology

- local content and digital art and design

A transdisciplinary and transversal scope will be given to this teaching focusing on creative processes and technology in order for students to apply their newly acquired knowledge in production of diversified creative work.

## Target Audiences

This teaching programme will target 25/30 university students from Arab States, as well as University students, teachers or professionals, interested in benefiting from a teaching session relating to science and technology.  It is specifically recommended to those persons who already have an experience or degree in the following fields:  design, publication, visual arts, media arts, multimedia, communication and journalism. The aim is to build multi-disciplinary learning community that will benefit from each other skills and knowledge.

## Teaching Staff

A network of universities and educational institutes with professors from different geo-cultural institutions will participate in the masterclass.  These stakeholders will encourage exchange and cooperation among universities and educational institutes in the regions, as well as cooperation opportunities between professionals.

The final objective is to associate to this programme the best Arab specialists as well as their peers at the international level in a field where exchange of information, excellency and experience, is essential.

# Academic Structure

This teaching programme will be divided into three main modules:

- Master class (Live contact teaching)- Practice and theory – Four week duration

- Optional studio studies (live contact teaching and online exercises) on digital design and authoring: web production and design, digital graphics, digital video and audio, (student can choose 1-2 studio courses with their tutor to be included in their personal study plan),

- Online tuition- Theory  – Three month duration

- Project development with online sessions -Practice - Two month duration

The first master class will be performed by four teachers and will take place in July 2005.

Online tuition will be made available through the UNESCO Knowledge Portal – Digi-Arts. Teachers will be answering to questions of the students at the end of the online tuition and will also be tutoring the students in their project development.

A first grade certificate of attendance (masterclass) will be given to the students having completed the three level teaching.

The languages used will be Arabic, English/or French.

The first master class will be organized on an experimental basis.  Between 25/30 students from different countries of the Arab world will be selected to attend and follow the four modules.  The Funding Committee of this programme will make fellowships for participation to the live master classes available.

Fees for attending the master class will be paid to the University and/or educational institute organizing it, which will be responsible for the local infrastructure and the technical facilities.

## International Network of Collaboration

This project will be promoted, executed and sponsored by the following Committees:

- Scientific Committee

- Organizers Committee

- Participating Institutions

- Collaborators’ Network

- Funding Committee

### Technological infrastructure

Master classes module

As mentioned before the University/Institution which will be hosting the Master classes will have to be equipped with the necessary technical infrastructure (hardware, software and new generation programmes for at least 30 students).

Online module

Through UNESCO Knowledge Portal DigiArts, online resources will be put at the disposal of the students in order to empowering them with the basic concepts of new media, Art and design. The students will be able to communicate with their teachers through chat sessions, discussion forums, and e-mail. The students who do not have their own technical equipment or internet connection will be able to have access to this environment through the Institutions involved in this programme.  This module will be available to a larger audience than the 25/30 selected students.

Within the framework of the online module each session will have the following teaching elements:

- A written document with images, graphics, videos

- Dynamic tutorials involving tools and proper documentation

- Bibliography in connection with the subjects taught

- Links to interesting sites and online articles

- Documentation, texts or articles that will serve as basic reference to students

- Other such as audiovisual materials.

- Group work tasks that produces study papers, art pieces, design proposal etc.

Expected results

It is expected in the short term to train around 30 students each year through two six months sessions. Individual and independent computer science students are well positioned to provide perspectives that challenge mainstream thinking.

Promote the use and creation of digital tools for capacity building in the field of cultural contents production, training and education, industry and leisure as Information and Communication Technologies opens completely new opportunities for young people.

This programme should reach all the Arab States through the establishment of UNESCO Chairs at University and Training Institutes levels.

Promote a networking of exchanges among new generation of specialists in the Arab region and a viable cooperation between Universities. Since a similar project is being launched for Latin America and the Caribbean, it is expected to promote south/south and inter-regional cooperation in the field of Art/design/science and technology.

This programme will be tailor made to young people living in the Arab Region in order to expand opportunities that Information and Communication Technologies offer in our Information Society.